## backend
Unit test #1
Test Details
|  |  | Name | Testing Main menu buttons | Created by: | DVFurnika20
|  |  | Description | Tested the Main menu buttons | Created on: | 2022-11-15
| ID | Test name | Functionality | Responsibility | Automation status | Deadline | Status | Date of Completion | Test Case #
| 1 | Choose option Play | Starting the game on click | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 9th | 1
| 3 | Choose option Info | Opening a window showing the rules and the controls of the game | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 9th | 2
| 4 | Choose option Exit | Closing the game | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 9th | 3
Unit test #2
Test Details
|  |  | Name | Displaying map, GUI, cities and other | Created by: | DVFurnika20
|  |  | Description | Tested different displays after starting the game | Created on: | 2022-11-15
| ID | Test name | Functionality | Responsibility | Automation status | Deadline | Status | Date of Completion | Test Case #
| 1 | Display map | Displaying map on screen | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 7th | 4
| 2 | Display GUI | Displaying progress in top-left corner | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 7th | 5
| 3 | Display cities on map with accurate hitboxes | Displaying the cities with accurate hitboxes on the map | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 7th | 6
| 4 | Display starting quiz window | Open the first city's quiz window on start | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 7th | 7
Unit test #3
Test Details
|  |  | Name | Traveling | Created by: | DVFurnika20
|  |  | Description | Tested functionality of traveling to different cities across the map | Created on: | 2022-11-15
| ID | Test name | Functionality | Responsibility | Automation status | Deadline | Status | Date of Completion | Test Case #
| 1 | Travel to non-visited cities | Traveling to cities that haven't been visited before | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 10th | 8
| 2 | Cost of travelling to a city | Points being taken when travelling to a city on the map | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 10th | 9
Unit test #4
Test Details
|  |  | Name | Quiz window | Created by: | DVFurnika20
|  |  | Description | Tested functionality of the quiz window | Created on: | 2022-11-15
| ID | Test name | Functionality | Responsibility | Automation status | Deadline | Status | Date of Completion | Test Case #
| 1 | Quiz window display | Opening quiz window when traveling to a city on the map | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 13th | 10
| 2 | Choosing correct option in quiz | Adding total points upon guessing the correct answer of the quiz | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 13th | 11
| 3 | Choosing wrong option in quiz | Continuing the game without gaining or losing points when answering to the quiz | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 13th | 12
Unit test #5
Test Details
|  |  | Name | GUI testing | Created by: | DVFurnika20
|  |  | Description | Tested functionality of the GUI | Created on: | 2022-11-15
| ID | Test name | Functionality | Responsibility | Automation status | Deadline | Status | Date of Completion | Test Case #
| 1 | Total point count | Displaying the total amount of points the player possesses at the moment | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 16th | 13
| 2 | Current city location | Displaying the city that the player is located on | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 16th | 14
| 3 | Count of cities already visited | Displaying the count of cities visited out of the total amount on the map | MMPetrov20, DSChebotarev20 | By hand | 20th November | pass | Nov 16th | 15

## frontend
Unit test #1
Test Details
|  |  | Name | Design Start menu buttons | Created by | DVFurnika20
|  |  | Description | Designed Start menu buttons | Created on | 2022-11-15
| ID | Test name | Responsibility | Automation status | Deadline | Status | Date of Completion | Test Case #
| 1 | Design the option Play | MMPetrov20 | By hand | 20th November | pass | Nov 9th | 1
| 2 | Design the option Rules and controls | MMPetrov20 | By hand | 20th November | pass | Nov 9th | 2
| 3 | Design the option Exit | MMPetrov20 | By hand | 20th November | pass | Nov 9th | 3
Unit test #2
Test Details
|  |  | Name | Confirm and Deny buttons | Created by | DVFurnika20
|  |  | Description | Designed the buttons used for traveling to a city | Created on | 2022-11-15
| ID | Test name | Responsibility | Automation status | Deadline | Status | Date of Completion | Test Case #
| 1 | Design the Confirm button | MMPetrov20 | By hand | 20th November | pass | Nov 5th | 4
| 2 | Design the Deny button | MMPetrov20 | By hand | 20th November | pass | Nov 5th | 5
| 3 | Design the hover effects for the buttons | MMPetrov20 | By hand | 20th November | pass | Nov 5th | 6
Unit test #3
Test Details
|  |  | Name | Quiz windows and GUI | Created by | DVFurnika20
|  |  | Description | Designed Quiz windows and animations | Created on | 2022-11-15
| ID | Test name | Responsibility | Automation status | Deadline | Status | Date of Completion | Test Case #
| 1 | Design Quiz windows for different cities | MMPetrov20, DSChebotarev20, MDVasilev20 | By hand | 20th November | pass | Nov 10th | 7
| 2 | Design animations on appearance and disappearance of the quiz window | MMPetrov20 | By hand | 20th November | pass | Nov 10th | 8
| 3 | Design GUI displaying progress | MMPetrov20 | By hand | 20th November | pass | Nov 10th | 9